## Raw_Ticket_Data
Request Recieved | Commitment | Assignee | Task Type | Priority | Ticket # | Summary | Status | Start Date | ETA | Closed Date | Sprint | Notes | Cycle Time (Days) | Forecast Accuracy (ETA)
Before | Committed | Dev 3 | Support Task | P2 (High) | EXP-1023 | Fix deployment failure in staging pipeline | New
Before | Committed | Dev 5 | Task | P3 (Med) | EXP-1047 | Update Terraform module for S3 encryption | Closed | 2025-10-22 | 2025-11-05 | 2025-11-06 | Sprint 2 |  | 16 | Late
Before | Committed | Dev 1 | Task | P4 (Low) | EXP-1091 | Investigate intermittent API timeout errors | Closed | 2025-10-23 | 2025-11-04 | 2025-11-04 | Sprint 1 |  | 13 | On time
Before | Committed | Dev 2 | Task | P1 (Critical) | EXP-1112 | Rotate expired service account credentials | Closed | 2025-10-22 | 2025-11-05 | 2025-11-05 | Sprint 2 |  | 15 | On time
Before | Committed | Dev 4 | Task | P3 (Med) | EXP-1138 | Enable logging for failed Lambda executions | New
Before | Committed | Dev 2 | Task | P2 (High) | EXP-1184 | Clean up unused feature flags | Closed | 2025-10-31 | 2025-11-04 | 2025-11-04 | Sprint 1 |  | 5 | On time
Before | Committed | Dev 4 | Task | P4 (Low) | EXP-1219 | Update CI runner to latest image version | Closed | 2025-10-23 | 2025-11-03 | 2025-11-02 | Sprint 1 |  | 11 | Early
Before | Committed | Dev 3 | Support Task | P2 (High) | EXP-1245 | Fix broken link in internal runbook | Closed | 2025-10-25 | 2025-10-30 | 2025-10-30 | Sprint 1 |  | 6 | On time
Before | Committed | Dev 1 | Task | P1 (Critical) | EXP-1277 | Investigate high memory usage on prod node | New
Before | Committed | Dev 5 | Task | P3 (Med) | EXP-1296 | Add alert for failed nightly batch job | Closed | 2025-10-22 | 2025-11-02 | 2025-11-02 | Sprint 1 |  | 12 | On time
Before | Committed | Dev 1 | Task | P4 (Low) | EXP-1321 | Upgrade Kubernetes cluster minor version | Closed | 2025-10-28 | 2025-11-02 | 2025-11-02 | Sprint 1 |  | 6 | On time
Before | Committed | Dev 3 | Task | P2 (High) | EXP-1350 | Resolve permission issue with secrets manager | On Hold | 2025-10-29 | 2025-11-14 |  |  | Pending external dependency
Before | Uncommitted | Dev 4 | Support Task | P3 (Med) | EXP-1389 | Document rollback steps for payment service | Closed | 2025-10-30 | 2025-11-18 | 2025-11-15 | Sprint 2 |  | 17 | Early
Before | Uncommitted | Dev 5 | Support Task | P1 (Critical) | EXP-1413 | Fix flaky integration test in CI | Closed | 2025-10-31 | 2025-11-19 | 2025-11-19 | Sprint 3 |  | 20 | On time
Before | Committed | Dev 2 | Task | P4 (Low) | EXP-1437 | Investigate delayed message processing in queue | New
Before | Committed | Dev 4 | Support Task | P2 (High) | EXP-1462 | Add retry logic to webhook handler | Closed | 2025-11-03 | 2025-11-20 | 2025-11-20 | Sprint 3 |  | 18 | On time
Before | Committed | Dev 2 | Task | P3 (Med) | EXP-1488 | Update autoscaling thresholds for API service | Closed | 2025-11-04 | 2025-11-12 | 2025-11-12 | Sprint 2 |  | 9 | On time
Before | Committed | Dev 5 | Support Task | P3 (Med) | EXP-1514 | Fix incorrect environment variable in prod | Closed | 2025-11-03 | 2025-11-20 | 2025-11-20 | Sprint 3 |  | 18 | On time
Before | Committed | Dev 3 | Support Task | P1 (Critical) | EXP-1541 | Review and update deployment approval process | New
Before | Committed | Dev 1 | Task | P4 (Low) | EXP-1569 | Investigate missing logs from worker service | Closed | 2025-11-06 | 2025-11-26 | 2025-11-26 | Sprint 3 |  | 21 | On time
Before | Committed | Dev 5 | Task | P2 (High) | EXP-1593 | Update monitoring dashboard for latency metrics | Closed | 2025-11-07 | 2025-11-14 | 2025-11-14 | Sprint 2 |  | 8 | On time
Before | Committed | Dev 3 | Task | P1 (Critical) | EXP-1620 | Fix failed database migration in staging | Closed | 2025-10-25 | 2025-11-04 | 2025-11-04 | Sprint 1 |  | 11 | On time
Before | Committed | Dev 1 | Task | P3 (Med) | EXP-1648 | Add health check endpoint to auth service | New
Before | Committed | Dev 2 | Support Task | P4 (Low) | EXP-1675 | Clean up deprecated IAM roles | Closed | 2025-11-08 | 2025-11-08 | 2025-11-08 | Sprint 2 |  | 1 | On time
Before | Committed | Dev 4 | Support Task | P2 (High) | EXP-1699 | Investigate spike in 500 errors after release | WIP | 2025-11-06 | 2025-11-26
Before | Committed | Dev 2 | Task | P3 (Med) | EXP-1724 | Update Helm chart values for prod | WIP | 2025-11-12 | 2025-12-04
Before | Committed | Dev 1 | Task | P1 (Critical) | EXP-1746 | Fix cache invalidation issue | New
Before | Committed | Dev 5 | Support Task | P4 (Low) | EXP-1778 | Document on-call escalation procedure | Closed | 2025-11-14 | 2025-12-09 | 2025-12-09 | Sprint 4 |  | 26 | On time
Before | Committed | Dev 4 | Task | P2 (High) | EXP-1801 | Investigate slow startup time for service | Closed | 2025-11-12 | 2025-12-04 | 2025-12-04 | Sprint 4 |  | 23 | On time
After | Uncommitted | Dev 3 | Task | P3 (Med) | EXP-1827 | Add alert for disk space threshold | WIP | 2025-11-17 | 2025-12-10
After | Uncommitted | Dev 4 | Task | P4 (Low) | EXP-1852 | Fix broken dependency in build pipeline | New
After | Uncommitted | Dev 5 | Support Task | P1 (Critical) | EXP-1876 | Update README for deployment repo | Closed | 2025-12-01 | 2025-12-11 | 2025-12-12 | Sprint 4 |  | 12 | Late
After | Uncommitted | Dev 3 | Task | P2 (High) | EXP-1904 | Investigate failed scheduled job | WIP | 2025-11-19 | 2025-12-12
After | Uncommitted | Dev 5 | Task | P3 (Med) | EXP-1931 | Fix typo in environment configuration | New
After | Uncommitted | Dev 1 | Support Task | P4 (Low) | EXP-1959 | Update secret rotation schedule | WIP | 2025-11-19 | 2025-12-12
After | Uncommitted | Dev 2 | Support Task | P2 (High) | EXP-1983 | Investigate dropped events in analytics pipeline | Closed | 2025-12-02 | 2025-12-16 | 2025-12-16 | Sprint 4 |  | 15 | On time
After | Uncommitted | Dev 4 | Task | P1 (Critical) | EXP-2010 | Add timeout configuration to external API calls | WIP | 2025-11-24 | 2025-12-17
After | Uncommitted | Dev 2 | Support Task | P3 (Med) | EXP-2036 | Fix misconfigured load balancer rule | New
After | Uncommitted | Dev 4 | Task | P4 (Low) | EXP-2064 | Update incident postmortem template | Closed | 2025-12-12 | 2025-12-16 | 2025-12-16 | Sprint 4 |  | 5 | On time
After | Uncommitted | Dev 3 | Support Task | P2 (High) | EXP-2089 | Investigate inconsistent cache behavior | WIP | 2025-11-26 | 2025-12-19
After | Uncommitted | Dev 1 | Support Task | P3 (Med) | EXP-2117 | Fix access issue for new service account | Closed | 2025-12-11 | 2025-12-19 | 2025-12-19 | Sprint 5 |  | 9 | On time
After | Uncommitted | Dev 5 | Task | P1 (Critical) | EXP-2142 | Add monitoring for CPU throttling | New
After | Uncommitted | Dev 1 | Task | P4 (Low) | EXP-2168 | Update dependency versions for security patch | Closed | 2025-12-20 | 2025-12-23 | 2025-12-23 | Sprint 5 |  | 4 | On time
After | Uncommitted | Dev 3 | Task | P2 (High) | EXP-2194 | Fix failed canary deployment | WIP | 2025-11-29 | 2025-12-24
After | Uncommitted | Dev 4 | Task | P3 (Med) | EXP-2221 | Document recovery steps for Redis outage | New
After | Uncommitted | Dev 5 | Support Task | P4 (Low) | EXP-2249 | Investigate alert noise from monitoring tool | WIP | 2025-12-01 | 2025-12-26
After | Uncommitted | Dev 2 | Support Task | P1 (Critical) | EXP-2273 | Update tagging standards for cloud resources | Closed | 2025-12-20 | 2025-12-30 | 2025-12-23 | Sprint 5 |  | 4 | Early
After | Uncommitted | Dev 4 | Task | P2 (High) | EXP-2298 | Fix missing environment variable in CI | Closed | 2025-12-15 | 2025-12-26 | 2025-12-26 | Sprint 5 |  | 12 | On time
After | Uncommitted | Dev 2 | Task | P3 (Med) | EXP-2315 | Investigate failed deployment rollback | Closed | 2025-12-18 | 2026-01-02 | 2026-01-02 | Sprint 6 |  | 16 | On time
After | Uncommitted | Dev 5 | Task | P4 (Low) | EXP-2342 | Update build cache configuration | New
After | Uncommitted | Dev 3 | Task | P2 (High) | EXP-2368 | Fix incorrect timeout setting in ingress | Closed | 2025-12-05 | 2026-01-04 | 2026-01-05 | Sprint 6 |  | 32 | Late
After | Uncommitted | Dev 1 | Task | P1 (Critical) | EXP-2391 | Add alert for message queue backlog | WIP | 2025-12-01 | 2025-12-26
After | Uncommitted | Dev 5 | Task | P3 (Med) | EXP-2417 | Update service documentation for new endpoint | WIP | 2025-12-08 | 2026-01-06
After | Uncommitted | Dev 3 | Task | P4 (Low) | EXP-2440 | Fix flaky smoke test in staging | New
After | Uncommitted | Dev 1 | Task | P2 (High) | EXP-2469 | Investigate pod restart loop in prod | Closed | 2025-12-26 | 2026-01-07 | 2026-01-07 | Sprint 6 |  | 13 | On time
After | Uncommitted | Dev 2 | Task | P3 (Med) | EXP-2493 | Clean up unused environment variables | WIP | 2025-12-10 | 2026-01-08
After | Uncommitted | Dev 4 | Support Task | P1 (Critical) | EXP-2521 | Update rate limiting configuration | New
After | Uncommitted | Dev 2 | Support Task | P4 (Low) | EXP-2548 | Fix permissions issue with artifact registry | WIP | 2025-12-10 | 2026-01-08
After | Uncommitted | Dev 1 | Task | P2 (High) | EXP-2576 | Investigate missing metrics in monitoring tool | Closed | 2025-11-12 | 2025-11-19 | 2025-11-19 | Sprint 3 |  | 8 | On time
After | Uncommitted | Dev 5 | Support Task | P3 (Med) | EXP-2602 | Add logging for authentication failures | Closed | 2025-11-15 | 2025-11-21 | 2025-11-21 | Sprint 3 |  | 7 | On time
After | Uncommitted | Dev 4 | Task | P4 (Low) | EXP-2637 | Update CI pipeline to support parallel jobs | New | 45968 | 45988 | 45982 | Sprint 3 |  | 15 | Early
After | Uncommitted | Dev 3 | Support Task | P1 (Critical) | EXP-2664 | Fix broken cron schedule | Closed | 2025-11-12 | 2025-11-21 | 2025-11-22 | Sprint 3 |  | 11 | Late
After | Uncommitted | Dev 4 | Support Task | P2 (High) | EXP-2689 | Investigate slow database queries | Closed | 2025-11-11 | 2025-11-27 | 2025-11-21 | Sprint 3 |  | 11 | Early
After | Uncommitted | Dev 5 | Task | P3 (Med) | EXP-2715 | Update autoscaling policy for worker service | Closed | 2025-11-25 | 2025-12-03 | 2025-12-03 | Sprint 4 |  | 9 | On time
After | Uncommitted | Dev 3 | Task | P4 (Low) | EXP-2741 | Fix failed secret injection in deployment | New
After | Uncommitted | Dev 5 | Task | P2 (High) | EXP-2768 | Document disaster recovery test results | Closed | 2025-11-07 | 2025-11-27 | 2025-11-21 | Sprint 3 |  | 15 | Early
After | Uncommitted | Dev 1 | Task | P1 (Critical) | EXP-2794 | Investigate inconsistent feature flag behavior | WIP | 2025-12-18 | 2026-01-16
After | Uncommitted | Dev 2 | Support Task | P3 (Med) | EXP-2820 | Add alert for error rate threshold | New
After | Uncommitted | Dev 4 | Support Task | P4 (Low) | EXP-2846 | Update deployment script for new repo structure | WIP | 2025-12-23 | 2026-01-19
After | Uncommitted | Dev 2 | Task | P2 (High) | EXP-2873 | Fix service startup failure in staging | Closed | 2025-12-31 | 2026-01-20 | 2026-01-20 | Sprint 6 |  | 21 | On time
After | Uncommitted | Dev 4 | Task | P3 (Med) | EXP-2899 | Clean up unused Docker images | WIP | 2025-11-06 | 2025-11-26
After | Uncommitted | Dev 3 | Task | P1 (Critical) | EXP-2924 | Investigate network latency between services | New
After | Uncommitted | Dev 1 | Support Task | P4 (Low) | EXP-2951 | Update Helm dependency versions | Closed | 2025-11-25 | 2025-12-04 | 2025-12-04 | Sprint 4 |  | 10 | On time
After | Uncommitted | Dev 5 | Task | P2 (High) | EXP-2978 | Fix incorrect health check path | WIP | 2025-11-12 | 2025-12-04
After | Uncommitted | Dev 1 | Task | P3 (Med) | EXP-3004 | Add monitoring for memory saturation | WIP | 2025-11-17 | 2025-12-10
After | Uncommitted | Dev 3 | Task | P4 (Low) | EXP-3030 | Update runbook for incident response | New
After | Uncommitted | Dev 4 | Task | P1 (Critical) | EXP-3057 | Investigate authentication token expiration issue | Closed | 2025-12-02 | 2025-12-12 | 2025-12-12 | Sprint 4 |  | 11 | On time
After | Uncommitted | Dev 5 | Task | P2 (High) | EXP-3083 | Fix broken alert notification channel | Closed | 2025-11-17 | 2025-12-10 | 2025-12-19 | Sprint 5 |  | 33 | Late
After | Uncommitted | Dev 2 | Support Task | P3 (Med) | EXP-3110 | Update infrastructure diagram | New
After | Uncommitted | Dev 4 | Support Task | P4 (Low) | EXP-3136 | Investigate delayed log ingestion | WIP | 2025-11-17 | 2025-12-10
After | Uncommitted | Dev 2 | Task | P2 (High) | EXP-3162 | Add retry logic to batch processing job | Closed | 2025-12-10 | 2025-12-12 | 2025-12-12 | Sprint 4 |  | 3 | On time
After | Uncommitted | Dev 5 | Support Task | P1 (Critical) | EXP-3189 | Fix misconfigured firewall rule | Closed | 2025-11-26 | 2025-12-19 | 2025-12-19 | Sprint 5 |  | 24 | On time
After | Uncommitted | Dev 3 | Task | P3 (Med) | EXP-3214 | Update dependency versions for vulnerability fix | Cancelled |  |  |  |  | no longer needed: duplicate
After | Uncommitted | Dev 1 | Support Task | P4 (Low) | EXP-3240 | Investigate service crash during peak traffic | New
After | Uncommitted | Dev 5 | Support Task | P2 (High) | EXP-3267 | Fix incorrect environment mapping in CI | Closed | 2025-11-30 | 2025-12-12 | 2025-12-12 | Sprint 4 |  | 13 | On time
After | Uncommitted | Dev 3 | Task | P3 (Med) | EXP-3293 | Add dashboard for deployment frequency | WIP | 2025-12-08 | 2026-01-06
After | Uncommitted | Dev 1 | Task | P1 (Critical) | EXP-3321 | Update on-call schedule documentation | WIP | 2025-12-10 | 2026-01-08
After | Uncommitted | Dev 2 | Task | P4 (Low) | EXP-3348 | Investigate duplicate events in data pipeline | New
After | Uncommitted | Dev 4 | Task | P2 (High) | EXP-3374 | Fix broken deployment approval step | Closed | 2025-11-29 | 2025-12-12 | 2025-12-15 | Sprint 4 |  | 17 | Late
After | Uncommitted | Dev 2 | Support Task | P3 (Med) | EXP-3401 | Update tagging for cost allocation | Closed | 2025-12-31 | 2026-01-19 | 2026-01-19 | Sprint 6 |  | 20 | On time
After | Uncommitted | Dev 1 | Support Task | P4 (Low) | EXP-3427 | Investigate failed health checks after deploy | On Hold | 2025-11-06 | 2025-11-26 |  |  | blocked: waiting on service team
After | Uncommitted | Dev 5 | Task | P1 (Critical) | EXP-3452 | Add alert for API latency spike | New
After | Uncommitted | Dev 4 | Task | P2 (High) | EXP-3479 | Fix incorrect container resource limits | Closed | 2025-12-30 | 2026-01-14 | 2026-01-14 | Sprint 6 |  | 16 | On time
After | Uncommitted | Dev 3 | Task | P2 (High) | EXP-3505 | Update secrets manager access policy | Closed | 2026-01-05 | 2026-01-17 | 2026-01-17 | Sprint 6 |  | 13 | On time
After | Uncommitted | Dev 4 | Task | P2 (High) | EXP-3532 | Investigate unexpected pod evictions | Closed | 2026-01-10 | 2026-01-14 | 2026-01-14 | Sprint 6 |  | 5 | On time
After | Uncommitted | Dev 5 | Task | P3 (Med) | EXP-3558 | Fix build failure due to version mismatch | WIP | 2025-12-08 | 2026-01-06
After | Uncommitted | Dev 1 | Task | P3 (Med) | EXP-3584 | Investigate failed readiness probe after deployment | Closed | 2026-01-11 | 2026-01-14 | 2026-01-14 | Sprint 6 |  | 4 | On time
After | Uncommitted | Dev 2 | Task | P4 (Low) | EXP-3611 | Update CI pipeline to handle dependency caching | Closed | 2026-01-02 | 2026-01-14 | 2026-01-14 | Sprint 6 |  | 13 | On time
After | Committed | Dev 3 | Task | P1 (Critical) | EXP-1111 | Hire Erika since she is the best Scrum Master turned Data Anaylst | Closed | 2026-01-14 | 2026-01-14 | 2026-01-14 | Sprint 6 |  | 1 | On time

## Kanban_Metrics
Entire Team Metrics |  | Throughput (Tasks closed within time Period) |  | By Team Member
Average Cycle Time (Days) | 12.6007 | Sprint 1 (Oct. 22 - Nov. 4) | 7 | Developer | Avg. Cycle Time (DAYS) | Current WIP | Closed PI Tickets
Current WIP | 22 | Sprint 2 (Nov. 5 - Nov. 18) | 6 | Dev 1 | 9.7778 | 5 | 9
Current Closed | 50 | Sprint 3 (Nov. 19 - Dec. 2) | 9 | Dev 2 | 11.0909 | 3 | 11
Current On Hold | 2 | Sprint 4 (Dec. 3 - Dec. 16) | 11 | Dev 3 | 12.3333 | 5 | 6
Current Open/New | 24 | Sprint 5 (Dec. 17 - Dec. 30) | 6 | Dev 4 | 13.4167 | 5 | 11
Cancelled | 1 | Sprint 6 (Dec. 31 - Jan 20) | 11 | Dev 5 | 16.3846 | 4 | 13
ETA Forecast Accuracy
On time | 39
Early | 6
Late | 6
No ETA Given | 0

## Delivery_Dashboard
Issue Details | Priority | Total | Open | WIP | On Hold | Closed
Total Number of Tasks Planned in PI-4 | P1 | 4 | 2 | 0 | 0 | 2
| P2 | 4 | 0 | 0 | 1 | 3
| P3 | 6 | 2 | 1 | 0 | 3
| P4 | 5 | 1 | 0 | 0 | 4
| Total | 19 | 5 | 1 | 1 | 12
Number of Issues created AFTER planning | P1 | 8 | 3 | 4 | 0 | 1
| P2 | 15 | 0 | 3 | 0 | 12
| P3 | 12 | 2 | 7 | 0 | 3
| P4 | 10 | 7 | 0 | 0 | 3
| Total | 45 | 12 | 14 | 0 | 19
Total Number of Support Tasks | Total | 33 | 7 | 7 | 1 | 18
Planned Tasks (bar chart)
|  | Open | WIP | On Hold | Closed
| P1 | 2 | 0 | 0 | 2
| P2 | 0 | 0 | 1 | 3
| P3 | 2 | 1 | 0 | 3
| P4 | 1 | 0 | 0 | 4
Unplanned Tasks (bar chart)
|  | Open | WIP | On Hold | Closed
| P1 | 3 | 4 | 0 | 1
| P2 | 0 | 3 | 0 | 12
| P3 | 2 | 7 | 0 | 3
| P4 | 7 | 0 | 0 | 3
Cycle Time Trend Over Time
| Throughput By Sprint |  |  | Sprint |  | Avg Cycle Time
| Sprint 1 | 7 |  | Sprint 1 |  | 9.1429
| Sprint 2 | 6 |  | Sprint 2 |  | 11
| Sprint 3 | 9 |  | Sprint 3 |  | 14.3333
| Sprint 4 | 11 |  | Sprint 4 |  | 13.0909
| Sprint 5 | 6 |  | Sprint 5 |  | 14.3333
| Sprint 6 | 11 |  | Sprint 6 |  | 14

## Insights & Observations
Kanban Delivery Analytics Dashboard
Excel ¦ Data Modeling ¦ Flow Metrics
Insights below are based on sample Kanban ticket data and are intended to demonstrate analytical interpretation rather than reflect a real team’s performance.
Insight | Analysis
Cycle Time Trends | Based on the cycle time trend, cycle time remained stable across most sprints, with the lowest average cycle time observed in Sprint 1. Reviewing ticket mix and WIP levels during Sprint 1 may help identify practices that contributed to faster delivery and could be replicated in future sprints.
Status Distribution | Closed and In Progress tickets make up the majority of work, indicating steady throughput across the PI. A small number of On Hold items suggests limited external blockers. However, periodic review of these tickets may help prevent long-running stagnation.
Planned vs. Unplanned Work | The Planned vs Unplanned bar chart shows that unplanned work represents a consistent portion of total delivery, reducing planned capacity each sprint. This pattern highlights the importance of reserving buffer capacity during PI planning to maintain delivery predictability.
Priority Mix | Most completed tickets fall within Medium and High priority levels, with few Critical items observed. This suggests effective prioritization and minimal reactive work, allowing the team to focus on planned delivery rather than urgent interruptions.

## README
Kanban Delivery Analytics Dashboard
Excel ¦ Data Modeling ¦ Flow Metrics
Project Overview:
This dashboard is inspired by a real-world Kanban reporting solution I designed while supporting a DevOps team. For this project, I recreated the structure using synthetic data to focus on metric design, data modeling, and visualization best practices. The dashboard highlights workflow trends, delivery performance, and operational insights intended to support continuous improvement and stakeholder communication.
Business Problem:
Kanban teams often struggle to maintain visibility into work in progress, delivery predictability, and flow efficiency. Leadership typically requires clear, concise metrics to understand progress without disrupting team workflows.
Project Objectives:
> Track work status and flow using Kanban metrics > Analyze cycle time trends across sprints > Compare planned vs unplanned work > Provide clear, executive-friendly visualizations
Data Description:
The dataset consists of 99 synthetic Kanban tickets modeled after a DevOps team workflow. Each ticket includes key attributes used to analyze flow and delivery performance. Key fields include: > Status (New, WIP, Closed, On Hold, Cancelled) > Priority (P1-P4) > Sprint (Sprint 1-6) > Start Date, ETA, Close Date > Calculated Cycle Time
Metrics & Calculations
Key metrics were calculated using Excel formulas and include cycle time, throughput, forecast accuracy, and planned vs. unplanned work distribution.
Dashboard & Insights
The dashboard visualizes delivery performance through charts and summary metrics. Key insights are documented in a separate Insights & Observations tab to support data driven decision making.
Assumptions & Limitations
> Data is synthetic and for demonstration purposes > Sprint length is two weeks, except for Sprint 6, which is 3 weeks > Metrics are intended to illustrate trends rather than evaluate team performance
Tools Used
> Microsoft Excel > Tables and Charts > Excel Formulas (AVERAGEIFS, COUNTIFS, etc.)